## Sheet1
Project Code | Date item added to Register | Project | Risk Title | Risk Description | Business Category | PRB Category | Initial Consequence Score | Initial Likelihood Score | Initial Risk rating | Date of Inital Risk Rating | Control in place | Controlled Consequence Score | Controlled Likelihood Score | Controlled Risk Rating | Date of Controlled Risk Rating | Action Plan | Risk Owner | Implementation date | Last Review date | Action at last review (Do not delete past entries) | Next review Date | Current Review Status
VAG-2025 | 2025-03-15 | Vagabond Photography Ltd | Client revenue concentration | High dependence on 1–2 clients could reduce revenue stability if a key client leaves. | Financial | Financial | 5 | 4 | 20 | 2025-03-20 | Informal client pipeline and referrals | 4 | 3 | 12 | 2025-03-30 | Diversify client portfolio; introduce retainers; monthly revenue-by-client review. | Business Owner | 2025-05-14 | 2025-04-29 | Mitigation actions reviewed; progress tracked. | 2025-07-13 | In Progress
VAG-2025 | 2025-03-15 | Vagabond Photography Ltd | Cash-flow delays | Late payments or delayed invoicing may impact ability to meet operating costs. | Financial | Financial | 4 | 4 | 16 | 2025-03-20 | Manual invoicing and reminders | 3 | 3 | 9 | 2025-03-30 | Introduce deposit policy; automate invoicing and reminders; track DSO. | Finance/Admin | 2025-04-29 | 2025-04-29 | Mitigation actions reviewed; progress tracked. | 2025-07-13 | In Progress
VAG-2025 | 2025-03-15 | Vagabond Photography Ltd | Data loss / corruption | Loss of photo assets or client data may cause contractual and reputational damage. | Reputational / Data | Operational | 5 | 3 | 15 | 2025-03-20 | Local drive backups | 2 | 2 | 4 | 2025-03-30 | Implement cloud + offsite backups; quarterly restore testing. | IT / Operations | 2025-04-14 | 2025-04-29 | Mitigation actions reviewed; progress tracked. | 2025-07-13 | In Progress
VAG-2025 | 2025-03-15 | Vagabond Photography Ltd | GDPR non-compliance | Inadequate consent or storage controls may lead to GDPR breaches. | Legal/Compliance | Legal | 4 | 3 | 12 | 2025-03-20 | Basic privacy notice | 3 | 2 | 6 | 2025-03-30 | Formal consent forms; access controls; deletion schedule. | Compliance Lead | 2025-05-14 | 2025-04-29 | Mitigation actions reviewed; progress tracked. | 2025-07-13 | In Progress
VAG-2025 | 2025-03-15 | Vagabond Photography Ltd | Equipment failure during shoot | Failure of camera or lighting equipment could delay delivery. | Operational | Operational | 4 | 3 | 12 | 2025-03-20 | Routine checks | 3 | 2 | 6 | 2025-03-30 | Maintain backup gear; pre-shoot checklist. | Operations Lead | 2025-04-14 | 2025-04-29 | Mitigation actions reviewed; progress tracked. | 2025-07-13 | In Progress
VAG-2025 | 2025-03-15 | Vagabond Photography Ltd | Freelancer dependency | Over-reliance on freelancers could affect scheduling and quality. | Operational | Operational | 3 | 4 | 12 | 2025-03-20 | Small pool of freelancers | 2 | 3 | 6 | 2025-03-30 | Expand freelancer bench; standard onboarding. | Production Manager | 2025-05-14 | 2025-04-29 | Mitigation actions reviewed; progress tracked. | 2025-07-13 | In Progress
VAG-2025 | 2025-03-15 | Vagabond Photography Ltd | Scheduling conflicts | Overbooking may delay delivery and impact client satisfaction. | Operational | Operational | 3 | 4 | 12 | 2025-03-20 | Manual scheduling | 2 | 3 | 6 | 2025-03-30 | Adopt scheduling tool; weekly capacity review. | Project Coordinator | 2025-04-14 | 2025-04-29 | Mitigation actions reviewed; progress tracked. | 2025-07-13 | In Progress
VAG-2025 | 2025-03-15 | Vagabond Photography Ltd | Contract ambiguity | Unclear scope may lead to rework and reduced margins. | Legal/Compliance | Legal | 4 | 3 | 12 | 2025-03-20 | Basic contract template | 3 | 2 | 6 | 2025-03-30 | Standardise contract clauses; change request process. | Legal Advisor | 2025-04-29 | 2025-04-29 | Mitigation actions reviewed; progress tracked. | 2025-07-13 | In Progress
VAG-2025 | 2025-03-15 | Vagabond Photography Ltd | Client dissatisfaction | Quality or delivery issues may lead to complaints and loss of referrals. | Reputational | Reputational | 4 | 3 | 12 | 2025-03-20 | Informal feedback | 3 | 2 | 6 | 2025-03-30 | Quality checklist; post-project survey. | Customer Success | 2025-04-14 | 2025-04-29 | Mitigation actions reviewed; progress tracked. | 2025-07-13 | In Progress
VAG-2025 | 2025-03-15 | Vagabond Photography Ltd | Cybersecurity incident | Account compromise could result in data loss or fraud. | Operational / Data | Operational | 4 | 3 | 12 | 2025-03-20 | Basic password hygiene | 2 | 2 | 4 | 2025-03-30 | Enable MFA; password manager; incident response steps. | IT / Operations | 2025-05-14 | 2025-04-29 | Mitigation actions reviewed; progress tracked. | 2025-07-13 | In Progress
VAG-2025 | 2025-06-15 | Vagabond Photography Ltd | Adverse weather during outdoor shoots | Rain, wind, heat or cold during outdoor shoots could cause injury, equipment damage, or project delays. | Health & Safety | Health & Safety | 5 | 3 | 15 | 2025-06-20 | Basic weather checks | 3 | 2 | 6 | 2025-06-30 | Formal weather risk assessment; stop-work thresholds; PPE; rescheduling protocol. | Health & Safety Lead | 2025-07-15 | 2025-07-30 | H&S risk reviewed; controls agreed. | 2025-10-13 | In Progress
VAG-2025 | 2025-06-15 | Vagabond Photography Ltd | Slips, trips and falls on location | Uneven terrain, cables, or wet surfaces may lead to injuries during shoots. | Health & Safety | Health & Safety | 4 | 3 | 12 | 2025-06-20 | Informal cable awareness | 3 | 2 | 6 | 2025-06-30 | Site-specific risk assessment; cable covers; safety briefing before shoots. | Health & Safety Lead | 2025-07-15 | 2025-07-30 | H&S risk reviewed; controls agreed. | 2025-10-13 | In Progress
VAG-2025 | 2025-06-15 | Vagabond Photography Ltd | Manual handling injuries (equipment) | Lifting and transporting heavy photography equipment may cause musculoskeletal injuries. | Health & Safety | Health & Safety | 4 | 3 | 12 | 2025-06-20 | Experience-based handling | 3 | 2 | 6 | 2025-06-30 | Manual handling training; weight limits; trolleys; team lifts. | Health & Safety Lead | 2025-07-15 | 2025-07-30 | H&S risk reviewed; controls agreed. | 2025-10-13 | In Progress
VAG-2025 | 2025-06-15 | Vagabond Photography Ltd | Heat stress or cold exposure | Extended exposure to extreme temperatures may cause illness or reduced performance. | Health & Safety | Health & Safety | 4 | 3 | 12 | 2025-06-20 | Ad-hoc breaks and hydration | 3 | 2 | 6 | 2025-06-30 | Work-rest cycles; hydration plan; protective clothing; authority to stop work. | Health & Safety Lead | 2025-07-15 | 2025-07-30 | H&S risk reviewed; controls agreed. | 2025-10-13 | In Progress
VAG-2025 | 2025-06-15 | Vagabond Photography Ltd | Vehicle incidents during travel | Driving to locations with equipment may increase risk of road traffic accidents. | Health & Safety | Health & Safety | 5 | 2 | 10 | 2025-06-20 | Valid licence and insurance | 3 | 2 | 6 | 2025-06-30 | Journey planning; driver fatigue checks; vehicle inspections; no-phone policy. | Health & Safety Lead | 2025-07-15 | 2025-07-30 | H&S risk reviewed; controls agreed. | 2025-10-13 | In Progress
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
[9 empty] | 0 |  |  |  |  | 0
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This should start with project name letters: e.g C2C and the numbers should be in order. This is so that the risks can be added to corporate register nad moved around on this sheet without getting lost (so we don't rely on line numbers within the sheet)